## New Home Construction Timeline
NEW HOME CONSTRUCTION TIMELINE TEMPLATE
WBS | TASK NAME | START DATE | END DATE | DURATION IN DAYS
1 | PRE-CONSTRUCTION | 2016-09-15 | 2016-10-14 | 29
1.1 | Contracts | 2017-10-06 | 2017-10-24 | 18
1.2 | Financing | 2017-10-25 | 2017-10-29 | 4
2 | FOUNDATION | 2017-11-01 | 2017-11-13 | 12
2.1 | Layout, Pour, and Pin Footings | 2017-11-13 | 2017-11-15 | 2
2.2 | Block, Mortar, Sand Foundation | 2017-10-25 | 2017-12-05 | 41
3 | DRAW #1 | 2017-11-19 | 2017-12-10 | 21
3.1 | Steel and Lumber Delivery | 2017-10-29 | 2017-12-09 | 41
3.2 | Waterproofing and Drain Tile | 2017-11-22 | 2017-12-15 | 23
4 | FRAMING | 2017-11-29 | 2017-12-20 | 21
4.1 | Set Steel | 2017-12-10 | 2017-12-22 | 12
4.2 | Deck Framing | 2017-12-10 | 2017-12-15 | 5
4.3 | Specialty Rough-Ins (Alarm, Cable, etc.) | 2017-12-10 | 2017-12-15 | 5
5 | ROOF | 2017-12-27 | 2017-12-30 | 3
5.1 | Roof Trusses | 2017-12-03 | 2017-12-21 | 18
5.2 | Roofing Paper and Shingles | 2018-01-03 | 2018-01-23 | 20
6 | DRAW #2 | 2018-01-03 | 2018-01-17 | 14
6.1 | Wall Framing | 2018-01-04 | 2018-01-13 | 9
6.2 | Windows and Doors | 2018-02-16 | 2018-03-11 | 23
7 | EXTERIOR FINISHES | 2018-01-19 | 2018-03-10 | 50
7.1 | Siding | 2018-02-03 | 2018-02-14 | 11
7.2 | Trim and Brick Veneer | 2018-01-18 | 2018-03-06 | 47
8 | PLUMBING/ELECTRICAL/HVAC | 2018-02-16 | 2018-02-23 | 7
8.1 | Plumbing/Electrical/HVAC Rough-In | 2018-02-25 | 2018-03-09 | 12
8.2 | Inspections | 2018-02-15 | 2018-02-17 | 2
9 | DRAW #3 | 2018-02-28 | 2018-04-14 | 45
9.1 | Frame Basement | 2018-03-21 | 2018-03-31 | 10
9.2 | Frame Bulkheads | 2018-02-28 | 2018-03-10 | 10
10 | INSULATION/DRYWALL | 2018-02-28 | 2018-03-18 | 18
10.1 | Caulk, Air Seal, Draft and Fire Stop, Insulation | 2018-05-03 | 2018-05-13 | 10
10.2 | Hang, Tape, Finish, and Sand Drywall | 2018-05-02 | 2018-05-03 | 1
11 | INTERIOR FINISHES | 2018-05-02 | 2018-05-05 | 3
11.1 | Interior Walls and Trim | 2018-05-03 | 2018-05-11 | 8
11.2 | Cabinetry and Countertops | 2018-05-09 | 2018-05-13 | 4
12 | DRAW #4 | 2018-05-13 | 2018-05-18 | 5
12.1 | Paint Cabinets and Doors | 2018-05-02 | 2018-05-02 | 0
12.2 | Switch and Plug Finishing | 2018-05-09 | 2018-06-05 | 27
13 | FLOORING | 2018-05-29 | 2018-06-10 | 12
13.1 | Tile and Hardwood Install, Sand, Stain, Seal | 2018-05-30 | 2018-06-10 | 11
13.2 | Carpet Install | 2018-05-31 | 2018-06-03 | 3
14 | FIXTURES AND APPLIANCES | 2018-06-01 | 2018-06-04 | 3
14.1 | Remaining Lights/Fans | 2018-06-02 | 2018-06-05 | 3
14.2 | Appliance Install | 2018-06-03 | 2018-06-06 | 3
15 | DRAW #5 | 2018-06-04 | 2018-06-07 | 3
15.1 | Door Hardware | 2018-06-05 | 2018-06-08 | 3
15.2 | Bath Hardware | 2018-06-06 | 2018-06-09 | 3
16 | LANDSCAPING/DESIGN | 2018-06-07 | 2018-06-10 | 3
16.1 | Patios, Porches, Decks, Drive and Walkways | 2018-06-08 | 2018-06-11 | 3
16.2 | Yard, Plants, Groundskeeping | 2018-06-09 | 2018-06-12 | 3
17 | FINAL DETAILS/CLOSEOUT | 2018-06-10 | 2018-06-13 | 3
17.1 | Final Walk-Through | 2018-06-11 | 2018-06-14 | 3
17.2 | Final Touch-Ups | 2018-06-12 | 2018-06-15 | 3
18 | FINAL DRAW | 2018-06-13 | 2018-06-16 | 3
18.1 | Cleaning | 2018-06-14 | 2018-06-17 | 3
18.2 | Move-In | 2018-06-15 | 2018-06-18 | 3
CLICK HERE TO CREATE IN SMARTSHEET

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.