## Office Renovation Calendar
OFFICE RENOVATION CONSTRUCTION CALENDAR TEMPLATE
PROJECT NAME |  | PROJECT MANAGER |  |  | START DATE
[5 empty] | 2025-09-22 | <--Enter date of Monday of first week.
PRIORITY | TASK NAME | START DATE | END DATE | DURATION | STATUS | % COMPLETE | ASSIGNED TO | COMMENTS | 2025-09-22 |  |  |  |  | 2025-09-29 |  |  |  |  | 2025-10-06 |  |  |  |  | 2025-10-13 |  |  |  |  | 2025-10-20 |  |  |  |  | 2025-10-27 |  |  |  |  | 2025-11-03 |  |  |  |  | 2025-11-10 |  |  |  |  | 2025-11-17 |  |  |  |  | 2025-11-24 |  |  |  |  | 2025-12-01 |  |  |  |  | 2025-12-08 |  |  |  |  | 2025-12-15 |  |  |  |  | 2025-12-22 |  |  |  |  | 2025-12-29 |  |  |  |  | 2026-01-05 |  |  |  |  | 2026-01-12 |  |  |  |  | 2026-01-19 |  |  |  |  | 2026-01-26 |  |  |  |  | 2026-02-02 |  |  |  |  | 2026-02-09 |  |  |  |  | 2026-02-16 |  |  |  |  | 2026-02-23 |  |  |  |  | 2026-03-02 |  |  |  |  | 2026-03-09 |  |  |  |  | 2026-03-16 |  |  |  |  | 2026-03-23 |  |  |  |  | 2026-03-30 |  |  |  |  | PRIORITY | STATUS
| Office Remodel |  | 0 | 1 |  |  |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | KEY | KEY
| Start Date |  |  | 1 |  | 75% | [142 empty] | Low | Not Started
Medium | Final Estimate Complete |  |  | 1 |  | 100% | [142 empty] | Medium | In Progress
High | Contract Signed |  |  | 1 |  | 50% | [142 empty] | High | Complete
Low | Permission to Schedule Work? |  |  | 1 |  | 10% | [143 empty] | On Hold
| Demo Prep |  |  | 1 | In Progress | [144 empty] | Overdue
| Appliance, Fixture and, Salvage |  |  | 1 | Complete
| Electrical - Cut Power and Install Temp Service |  |  | 1 | Overdue
| Safety Fence Delivery/Setup |  |  | 1 | In Progress
| Install Office/Safety Area (Plans Desk, First Aid, Phone) |  |  | 1 | On Hold
| Install Site Camera(s) |  |  | 1 | Not Started
| Demolition |  |  | 1
| Walls |  |  | 1
| Floors |  |  | 1
| Framing |  |  | 1
| Level/True Basement and Main Floor |  |  | 1
| Frame New Home and Addition |  |  | 1
| Plumbing |  |  | 1
| Ground Work |  |  | 1
| Rough In |  |  | 1
| Windows |  |  | 1
| Order Windows |  |  | 1
| Wrap Sills |  |  | 1
| Install Windows |  |  | 1
| HVAC |  |  | 1
| Ducting and Gas Piping |  |  | 1
| Fire System for Drywall |  |  | 1
| Electrical |  |  | 1
| Electrical-Rough In |  |  | 1
| Walkthrough |  |  | 1
| A/V |  |  | 1
| Low Voltage- CATV, CAT6, Tele |  |  | 1
| Speaker Pre-Wire |  |  | 1
| Alarm/Security Wiring |  |  | 1
| Insulation |  |  | 1
| Blow In |  |  | 1
| Bats |  |  | 1
| Rigid |  |  | 1
| Drywall |  |  | 1
| Delivery |  |  | 1
| Hang and Scrap |  |  | 1
| Tape |  |  | 1
| Prime |  |  | 1
| Touch Up If Needed |  |  | 1
| Hardwoods |  |  | 1
| Deliver/Acclimate |  |  | 1
| Install Hardwoods |  |  | 1
High | Stain |  |  | 1
High | Finish |  |  | 1
| Cure and Protect |  |  | 1
| Tile |  |  | 1
| Prep |  |  | 1
| Install |  |  | 1
| Install |  |  | 1
| Cabinets |  |  | 1
| Shared Space |  |  | 1
| Offices |  |  | 1
| Kitchenettes |  |  | 1
| Conference Rooms |  |  | 1
| Bath |  |  | 1
| Plumbing Hang Sinks |  |  | 1
| Install under Mount Sinks |  |  | 1
| Interior Doors |  |  | 1
| Delivery-Hang |  |  | 1
| Ship to Pre-Fin |  |  | 1
| Millwork |  |  | 1
| Millwork Material Delivery |  |  | 1
| Millwork Install |  |  | 1
| Interior Painting |  |  | 1
| Millwork Prep |  |  | 1
| Cleaning and Masking |  |  | 1
| Millwork Painting and Curing (Oil) |  |  | 1
| Interior Walls and Ceilings |  |  | 1
| Interior doors Hang and Hardware |  |  | 1
| Return from Pre-Fin Shop |  |  | 1
| Hang |  |  | 1
| Install Hardware |  |  | 1
| Appliances |  |  | 1
| Delivery |  |  | 1
| Install |  |  | 1
| Plumbing |  |  | 1
| Set Toilets, Sinks, etc. |  |  | 1
| Electrical |  |  | 1
| Trim Cans |  |  | 1
| Outlets and Switches |  |  | 1
| Surface Mount Fixtures |  |  | 1
| Bathroom Glass |  |  | 1
| Mirrors |  |  | 1
| Shower Doors |  |  | 1
| Final Inspections |  |  | 1
| Plumbing, Electrical, Mechanical |  |  | 1
| Final Inspection |  |  | 1
| Wrap Up |  |  | 1
| Punch List and Touch Up |  |  | 1
| Bath Accessories |  |  | 1
| Remove Tools |  |  | 1
| Remove Materials |  |  | 1
| Deliver Job Book (Sub List, Warranty/Install Paperwork, etc.) |  |  | 1
| Deliver Keys |  |  | 1
| Complete |  |  | 1
CLICK HERE TO CREATE IN SMARTSHEET
TODAY

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.