## Critical Path Tracking
CRITICAL PATH TRACKING TEMPLATE
Complete non-shaded fields, only. |  | START DATE | [5 empty] | 2021-01-17
|  | FINISH DATE excluding wknds & holidays | [5 empty] | 2021-03-30 | DURATION in days | 50
| – CRITICAL ACTIVITIES | [6 empty] | DURATION in days
|  | PREDECESSOR ACTIVITIES | [5 empty] | OPTIMISTIC | MOST LIKELY | PESSIMISTIC | EXPECTED | EARLY START | EARLY FINISH | LATE START | LATE FINISH
ID | ACTIVITY DESCRIPTION | PA – enter separately in columns | [5 empty] | MIN | AVG | MAX | DURATION | ES | EF | LS | LF | SLACK
1 | START | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
2 | Task 2 | 1 | [5 empty] | 3 | 4 | 5 | 4 | 0 | 4 | 0 | 4 | 0
3 | Task 3 | 1 | [5 empty] | 2 | 4 | 6 | 4 | 0 | 4 | 1.6667 | 5.6667 | 1.6667
4 | Task 4 | 2 | [5 empty] | 3 | 6 | 8 | 5.6667 | 4 | 9.6667 | 4 | 9.6667 | 0
5 | Task 5 | 1 | 2 | 3 |  |  |  | 2 | 4 | 6 | 4 | 4 | 8 | 5.6667 | 9.6667 | 1.6667
6 | Task 6 | 3 | 4 | 5 |  |  |  | 1 | 3 | 5 | 3 | 9.6667 | 12.6667 | 9.6667 | 12.6667 | 0
7 | Task 7 | 6 | [5 empty] | 4 | 8 | 10 | 7.3333 | 12.6667 | 20 | 12.6667 | 20 | 0
8 | Task 8 | 7 | [5 empty] | 1 | 3 | 5 | 3 | 20 | 23 | 20 | 23 | 0
9 | Task 9 | 6 | 7 | 8 |  |  |  | 1 | 3 | 5 | 3 | 23 | 26 | 26 | 29 | 3
10 | Task 10 | 8 | [5 empty] | 1 | 3 | 5 | 3 | 23 | 26 | 23 | 26 | 0
11 | Task 11 | 9 | 10 |  |  |  |  | 1 | 3 | 5 | 3 | 26 | 29 | 29 | 32 | 3
12 | Task 12 | 10 | [5 empty] | 1 | 3 | 5 | 3 | 26 | 29 | 26 | 29 | 0
13 | Task 13 | 12 | [5 empty] | 1 | 3 | 5 | 3 | 29 | 32 | 29 | 32 | 0
14 | Task 14 | 11 | 12 | 13 |  |  |  | 1 | 3 | 5 | 3 | 32 | 35 | 32 | 35 | 0
15 | Task 15 | 11 | 14 |  |  |  |  | 1 | 3 | 5 | 3 | 35 | 38 | 35 | 38 | 0
16 | Task 16 | 14 | 15 |  |  |  |  | 1 | 3 | 5 | 3 | 38 | 41 | 38 | 41 | 0
17 | Task 17 | 13 | 15 | 16 |  |  |  | 1 | 3 | 5 | 3 | 41 | 44 | 41 | 44 | 0
18 | Task 18 | 11 | 12 | 13 | 14 | 16 | 17 | 1 | 3 | 5 | 3 | 44 | 47 | 44 | 47 | 0
19 | Task 19 | 12 | 18 |  |  |  |  | 1 | 3 | 5 | 3 | 47 | 50 | 47 | 50 | 0
20 | FINISH | 18 | 19 | [7 empty] | 0 | 50 | 50 | 50 | 50 | 0
CLICK HERE TO CREATE IN SMARTSHEET
CALCULATIONS FOR CHART AREA
[17 empty] | PA EF | [5 empty] | SA | [19 empty] | SA LS | [19 empty] | ES | C | over | under | DURATION | over | under | SLACK | EVENTS | EVENTS | AXIS
[17 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 2 | 3 |  | 5 | [16 empty] | 0 | 1.6667 |  | 5.6667 | [15 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | -0.5
[17 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | 5 | [18 empty] | 4 | 5.6667 | [15 empty] | 0 | 4 | 1 | 1 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 0.5
[17 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 5 | 6 | [18 empty] | 5.6667 | 9.6667 | [14 empty] | 0 | #N/A | #N/A | #N/A | 4 | 2 | 2 | 1.6667 | #N/A | #N/A | 1.5
[17 empty] | 4 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 6 | [19 empty] | 9.6667 | [14 empty] | 4 | 5.6667 | 2.3333 | 2.6667 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 2.5
[17 empty] | 0 | 4 | 4 | 0 | 0 | 0 | [5 empty] | 6 | [19 empty] | 9.6667 | [14 empty] | 4 | #N/A | #N/A | #N/A | 4 | 2 | 2 | 1.6667 | #N/A | #N/A | 3.5
[17 empty] | 4 | 9.6667 | 8 | 0 | 0 | 0 | [6 empty] | 7 |  | 9 | [17 empty] | 12.6667 |  | 26 | [11 empty] | 9.6667 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 4.5
[17 empty] | 12.6667 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 8 | 9 | [18 empty] | 20 | 26 | [11 empty] | 12.6667 | 7.3333 | 2.6667 | 3.3333 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 5.5
[17 empty] | 20 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 9 | 10 | [18 empty] | 26 | 23 | [10 empty] | 20 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 6.5
[17 empty] | 12.6667 | 20 | 23 | 0 | 0 | 0 | [10 empty] | 11 | [19 empty] | 29 | [9 empty] | 23 | #N/A | #N/A | #N/A | 3 | 2 | 2 | 3 | #N/A | #N/A | 7.5
[17 empty] | 23 | 0 | 0 | 0 | 0 | 0 | [10 empty] | 11 | 12 | [18 empty] | 29 | 26 | [8 empty] | 23 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 8.5
[17 empty] | 26 | 26 | 0 | 0 | 0 | 0 | [13 empty] | 14 | 15 |  |  | 18 | [15 empty] | 32 | 35 |  |  | 44 |  |  | 26 | #N/A | #N/A | #N/A | 3 | 2 | 2 | 3 | #N/A | #N/A | 9.5
[17 empty] | 26 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 13 | 14 |  |  |  | 18 | 19 | [13 empty] | 29 | 32 |  |  |  | 44 | 47 |  | 26 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 10.5
[17 empty] | 29 | 0 | 0 | 0 | 0 | 0 | [13 empty] | 14 |  |  | 17 | 18 | [15 empty] | 32 |  |  | 41 | 44 |  |  | 29 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 11.5
[17 empty] | 29 | 29 | 32 | 0 | 0 | 0 | [14 empty] | 15 | 16 |  | 18 | [16 empty] | 35 | 38 |  | 44 |  |  | 32 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 12.5
[17 empty] | 29 | 35 | 0 | 0 | 0 | 0 | [15 empty] | 16 | 17 | [18 empty] | 38 | 41 |  |  |  | 35 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 13.5
[17 empty] | 35 | 38 | 0 | 0 | 0 | 0 | [16 empty] | 17 | 18 | [18 empty] | 41 | 44 |  |  | 38 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 14.5
[17 empty] | 32 | 38 | 41 | 0 | 0 | 0 | [17 empty] | 18 | [19 empty] | 44 |  |  | 41 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 15.5
[17 empty] | 29 | 29 | 32 | 35 | 41 | 44 | [18 empty] | 19 | 20 | [18 empty] | 47 | 50 | 44 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 16.5
[17 empty] | 29 | 47 | 0 | 0 | 0 | 0 | [19 empty] | 20 | [19 empty] | 50 | 47 | 3 | 2 | 2 | #N/A | #N/A | #N/A | 0 | #N/A | #N/A | 17.5
[17 empty] | 47 | 50 | 0 | 0 | 0 | 0 | [40 empty] | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 10 | 50 | 18.5

## BLANK - Critical Path Tracking
CRITICAL PATH TRACKING TEMPLATE
Complete non-shaded fields, only. |  | START DATE
|  | FINISH DATE excluding wknds & holidays | 0 | DURATION in days | 0
| – CRITICAL ACTIVITIES |  | DURATION in days
|  | PREDECESSOR ACTIVITIES | OPTIMISTIC | MOST LIKELY | PESSIMISTIC | EXPECTED | EARLY START | EARLY FINISH | LATE START | LATE FINISH
ID | ACTIVITY DESCRIPTION | PA – enter separately in columns | MIN | AVG | MAX | DURATION | ES | EF | LS | LF | SLACK
1 | START |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
2 | Task 2 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3 | Task 3 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
4 | Task 4 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
5 | Task 5 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
6 | Task 6 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
7 | Task 7 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
8 | Task 8 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
9 | Task 9 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
10 | Task 10 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
11 | Task 11 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
12 | Task 12 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
13 | Task 13 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
14 | Task 14 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
15 | Task 15 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
16 | Task 16 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
17 | Task 17 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
18 | Task 18 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
19 | Task 19 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
20 | FINISH |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
CALCULATIONS FOR CHART AREA
[12 empty] | PA EF | [5 empty] | SA | SA LS | ES | C | over | under | DURATION | over | under | SLACK | EVENTS | EVENTS | AXIS
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | -0.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 0.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 1.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 2.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 3.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 4.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 5.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 6.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 7.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 8.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 9.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 10.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 11.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 12.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 13.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 14.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 15.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 16.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 17.5
[12 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | 0 | 18.5

## Holidays
Enter Non-Working Holidays, below.
DATE | DESCRIPTION
2019-10-14 | Columbus Day
2019-11-11 | Veterans Day
2019-11-28 | Thanksgiving Day
2019-12-25 | Christmas Day
2020-01-01 | New Year's Day
2020-01-20 | Martin Luther King Jr.'s Birthday
2020-02-17 | Washington's Birthday
2020-05-25 | Memorial Day
2020-07-04 | Independence Day
2020-09-07 | Labor Day
2020-10-12 | Columbus Day
2020-11-11 | Veterans Day
2020-11-26 | Thanksgiving Day
2020-12-25 | Christmas Day
2021-01-01 | New Year's Day
2021-01-18 | Martin Luther King Jr.'s Birthday
2021-02-15 | Washington's Birthday
2021-05-31 | Memorial Day
2021-07-04 | Independence Day
2021-09-06 | Labor Day
2021-10-11 | Columbus Day
2021-11-11 | Veterans Day
2021-11-25 | Thanksgiving Day
2021-12-25 | Christmas Day

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.