## Software Migration Plan
SOFTWARE MIGRATION PLAN TEMPLATE
Project Name
TASK NAME | START | END | DURATION (days) | TASK OWNER | PERCENT OF TASK COMPLETE
PHASE 1 – SELF-ASSESSMENT
Define business vision | 2018-09-02 | 2018-09-02 | 1 |  | 100%
Identify skills | 2018-09-03 | 2018-09-03 | 1 |  | 100%
Decide whether to proceed | 2018-09-04 | 2018-09-04 | 1 |  | 100%
PHASE 1 – DEFINE OPPORTUNITY
Research market | 2018-09-05 | 2018-09-05 | 1 |  | 33%
Conduct interviews | 2018-09-06 | 2018-09-10 | 5 |  | 70%
Identify needed resources | 2018-09-11 | 2018-09-13 | 3 |  | 22%
Identify operating costs | 2018-09-13 | 2018-09-14 | 2 |  | 40%
PHASE 1 – EVALUATE POTENTIAL RISKS
Assess market size | 2018-09-15 | 2018-09-17 | 3 |  | 60%
Estimate competition | 2018-09-17 | 2018-09-18 | 2 |  | 0%
Assess needed resources | 2018-09-18 | 2018-09-19 | 2 |  | 0%
Determine financial requirements | 2018-09-19 | 2018-09-21 | 3 |  | 0%
Evaluate profitability | 2018-09-21 | 2018-09-22 | 2 |  | 0%
Review strategy | 2018-09-22 | 2018-09-23 | 2 |  | 25%
PHASE 2 – DEFINE MARKET
Access available research | 2018-09-23 | 2018-09-25 | 3 |  | 40%
Create market analysis | 2018-09-26 | 2018-09-29 | 4 |  | 25%
Implement market analysis | 2018-09-29 | 2018-10-01 | 3 |  | 33%
CLICK HERE TO CREATE IN SMARTSHEET

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.