## Example Construction Schedule
EXAMPLE CONSTRUCTION SCHEDULE
PROJECT NAME |  | PROJECT MANAGER |  |  | START DATE
Frisco Manufacturing Plant |  | Elizabeth Hotchkiss |  |  | 2025-01-05 | <--Enter date of Sunday of first week.
WBS | TASK NAME | START DATE | FINISH DATE | DURATION in days | PERCENTAGE COMPLETE | 2025-01-05 | [6 empty] | 2025-01-12 | [6 empty] | 2025-01-19 | [6 empty] | 2025-01-26 | [6 empty] | 2025-02-02 | [6 empty] | 2025-02-09 | [6 empty] | 2025-02-16 | [6 empty] | 2025-02-23 | [6 empty] | 2025-03-02 | [6 empty] | 2025-03-09 | [6 empty] | 2025-03-16 | [6 empty] | 2025-03-23 | [6 empty] | 2025-03-30 | [6 empty] | 2025-04-06 | [6 empty] | 2025-04-13 | [6 empty] | 2025-04-20 | [6 empty] | 2025-04-27 | [6 empty] | 2025-05-04 | [6 empty] | 2025-05-11 | [6 empty] | 2025-05-18 | [6 empty] | 2025-05-25 | [6 empty] | 2025-06-01 | [6 empty] | 2025-06-08 | [6 empty] | 2025-06-15 | [6 empty] | 2025-06-22 | [6 empty] | 2025-06-29 | [6 empty] | 2025-07-06 | [6 empty] | 2025-07-13
[6 empty] | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa
1 | Proposal and Documentation
2 | Design
2.1
2.2
2.3
2.4
2.5
2.6
2.7
2.8
2.9
2.10.
3 | Contracts / Bids
3.1
3.2
3.3
3.4
3.5
3.6
3.7
3.8
3.9
3.10.
4 | Permits
4.1
4.2
4.3
4.4
4.5
4.6
4.7
4.8
4.9
4.10.
5 | Inspections
5.1
5.2
5.3
5.4
5.5
5.6
5.7
5.8
5.9
5.10.
6 | Site Preparation | 2025-01-06 | 2025-01-28 | 23 | 45%
6.1
6.2
6.3
6.4
6.5
6.6
6.7
6.8
6.9
6.10.
6.1 | Site Surveying | 2025-01-06 | 2025-01-09 | 4 | 100% | bar: 2025-01-05 M to 2025-01-05 R
6.2 | Soil Testing | 2025-01-08 | 2025-01-14 | 6 | 100% | bar: 2025-01-05 R to 2025-01-12 T; 2025-02-02 R to 2025-02-02 Sa; 2025-02-16 R to 2025-02-16 Sa; 2025-03-02 R to 2025-03-02 Sa; 2025-03-16 R to 2025-03-16 Sa; 2025-03-30 R to 2025-03-30 Sa; 2025-04-13 R to 2025-04-13 Sa; 2025-04-27 R to 2025-04-27 Sa; 2025-05-11 R to 2025-05-11 Sa; 2025-05-25 R to 2025-05-25 Sa; 2025-06-08 R to 2025-06-08 Sa; 2025-06-22 R to 2025-06-22 Sa; 2025-07-06 R to 2025-07-06 Sa
6.3 | Site Plan Design | 2025-01-15 | 2025-01-20 | 6 | 18% | bar: 2025-01-12 W to 2025-01-19 M
6.4 | Site Clearing and Grading | 2025-01-20 | 2025-01-23 | 4 | 0% | bar: 2025-01-19 M to 2025-01-19 R
6.5 | Soil Compaction | 2025-01-24 | 2025-01-28 | 5 | 0% | bar: 2025-01-19 F to 2025-01-26 T
7 | Foundation / Framing
7.1
7.2
7.3
7.4
7.5
7.6
7.7
7.8
7.9
7.10.
8 | Roof / Exterior Finishes
8.1
8.2
8.3
8.4
8.5
8.6
8.7
8.8
8.9
8.10.
9 | Plumbing / Electrical / HVAC
9.1
9.2
9.3
9.4
9.5
9.6
9.7
9.8
9.9
9.10.
10 | Insulation / Drywall
10.1
10.2
10.3
10.4
10.5
10.6
10.7
10.8
10.9
10.10.
11 | Interior Finishes
11.1
11.2
11.3
11.4
11.5
11.6
11.7
11.8
11.9
11.10.
12 | Painting
12.1
12.2
12.3
12.4
12.5
12.6
12.7
12.8
12.9
12.10.
13 | Flooring
13.1
13.2
13.3
13.4
13.5
13.6
13.7
13.8
13.9
13.10.
14 | Fixtures / Appliances
14.1
14.2
14.3
14.4
14.5
14.6
14.7
14.8
14.9
14.10.
15 | Landscaping / Design
15.1
15.2
15.3
15.4
15.5
15.6
15.7
15.8
15.9
15.10.
16 | Final Details / Closure
16.1
16.2
16.3
16.4
16.5
16.6
16.7
16.8
16.9
16.10.
17 | Other
17.1
17.2
17.3
17.4
17.5
17.6
17.7
17.8
17.9
17.10.
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2025-01-05 Su to 2025-01-26 Sa
TODAY

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.