## Agile Project with Gantt
AGILE PROJECT WITH GANTT CHART TEMPLATE FOR MAC
| PROJECT NAME | PROJECT MANAGER |  | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS |  | PROJECT DELIVERABLE
| Product Release | Alex B. |  | 20% | 2028-09-02 | 2028-10-10 | 38
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DAYS | STATUS | STORY POINTS | STATUS KEY
| Sprint 1 |  | Alex B. |  | 2022-09-02 | 2022-09-03 | 1 | COMPLETE |  | COMPLETE
| Feature 1 |  | Frank C. |  | 2022-09-03 | 2022-09-07 | 4 | COMPLETE |  | IN PROGRESS
| Feature 2 |  | Jacob S. |  | 2022-09-07 | 2022-09-12 | 5 | COMPLETE |  | ON HOLD
| Feature 3 |  | Jacob S. |  | 2022-09-09 | 2022-09-11 | 2 | OVERDUE |  | OVERDUE
| Sprint 2 |  | Jacob S. |  | 2022-09-11 | 2022-09-15 | 4 | IN PROGRESS |  | NOT STARTED
| Feature 4 |  | Alex B. |  | 2022-09-16 | 2022-09-17 | 1 | IN PROGRESS
| Feature 5 |  | Frank C. |  | 2022-09-17 | 2022-09-21 | 4 | ON HOLD
| Feature 6 |  | Shari W. |  | 2022-09-22 | 2022-09-24 | 2 | NOT STARTED
| Sprint 3 |  | Shari W. |  | 2022-09-23 | 2022-09-27 | 4 | NOT STARTED
| Feature 7 |  | Alex B. |  | 2022-09-25 | 2022-09-29 | 4 | NOT STARTED
| Feature 8 |  | Kennedy K. |  | 2022-09-24 | 2022-10-02 | 8 | NOT STARTED
| Feature 9 |  | Jacob S. |  | 2022-10-02 | 2022-10-05 | 3 | NOT STARTED
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Agile Project with Gantt
AGILE PROJECT WITH GANTT CHART TEMPLATE FOR MAC
| PROJECT NAME | PROJECT MANAGER |  | OVERALL PROGRESS | START DATE | END DATE | TOTAL DAYS |  | PROJECT DELIVERABLE
0
SCOPE STATEMENT
AT RISK | TASK NAME | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START | FINISH | DAYS | STATUS | STORY POINTS | STATUS KEY
[7 empty] | 0 |  |  | COMPLETE
[7 empty] | 0 |  |  | IN PROGRESS
[7 empty] | 0 |  |  | ON HOLD
[7 empty] | 0 |  |  | OVERDUE
[7 empty] | 0 |  |  | NOT STARTED
0
0
0
0
0
0
0
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.