## SAMPLE - Project Burndown Chart
7.26
PROJECT BURNDOWN CHART TEMPLATE
PROJECT TITLE | [5 empty] | PROJECT MANAGER |  |  | DATE | VERSION NO. | PROJECT ID
[9 empty] | 00/00/0000 | 1.0 | PILOT-0628
User to complete only non-shaded cells in the tables below. Burndown data and chart will populate automatically.
BURNDOWN CHART
TASK INVENTORY |  |  | TASK COMPLETION LOG
|  |  |  | PROJECTED |  |  | ACTUAL |  |  | TASK COMPLETION (%)
Task ID | DESCRIPTION | WEIGHT (%) | DATE | Task ID | DATA | CUMULATIVE | Task ID | DATA | CUMULATIVE | PROJECTED | ACTUAL
1 | Product Planning | 11% | 2028-06-28 |  | 0% |  |  | 0% |  | 100% | 100%
2 | Project Definition | 7% | 2028-06-29 | 1 | 11% | 11% |  | 0% | 0% | 89% | 100%
3 | Product Prototyping | 6% | 2028-06-30 | 2 | 7% | 18% | 1 | 11% | 11% | 82% | 89%
4 | Initial Designs | 7% | 2028-07-01 | 3 | 6% | 24% | 2 | 7% | 18% | 76% | 82%
5 | Validation and Testing | 6% | 2028-07-02 | 4 | 7% | 31% | 3 | 6% | 24% | 69% | 76%
6 | Alpha Product Version | 11% | 2028-07-03 | 5 | 6% | 37% | 4 | 7% | 31% | 63% | 69%
7 | Beta Product Version | 8% | 2028-07-04 | 6 | 11% | 48% | 5 | 6% | 37% | 52% | 63%
8 | Validation and Testing | 9% | 2028-07-05 | 7 | 8% | 56% | 6 | 11% | 48% | 44% | 52%
9 | Beta Testing | 3% | 2028-07-06 | 8 | 9% | 65% | 7 | 8% | 56% | 35% | 44%
10 | Final QA | 4% | 2028-07-07 | 9 | 3% | 68% | 8 | 9% | 65% | 32% | 35%
11 | Product Release | 5% | 2028-07-08 | 10 | 4% | 72% | 9 | 3% | 68% | 28% | 32%
12 | User Research | 8% | 2028-07-09 | 11 | 5% | 77% | 10 | 4% | 72% | 23% | 28%
13 | Customer Feedback | 7% | 2028-07-10 | 12 | 8% | 85% | 11 | 5% | 77% | 15% | 23%
14 | Next Iteration | 6% | 2028-07-11 | 13 | 7% | 92% | 12 | 8% | 85% | 8% | 15%
15 | Next Iteration QA | 2% | 2028-07-12 | 14 | 6% | 98% | 13 | 7% | 92% | 2% | 8%
|  |  | 2028-07-13 | 15 | 2% | 100% | 14 | 6% | 98% | 0% | 2%
|  |  | 2028-07-14 |  | 0% | 100% | 15 | 2% | 100% | #N/A | 0%
APPLIED WEIGHT % MUST EQUAL 100 > |  | 100%
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
DATE = [DATE, row above]+1

## BLANK - Project Burndown Chart
PROJECT BURNDOWN CHART TEMPLATE
PROJECT TITLE | [5 empty] | PROJECT MANAGER |  |  | DATE | VERSION NO. | PROJECT ID
[9 empty] | 00/00/0000 | 1.0 | PILOT-0628
User to complete only non-shaded cells in the tables below. Burndown data and chart will populate automatically.
BURNDOWN CHART
User to complete only non-shaded cells in the tables below. Burndown data and chart will populate automatically.
TASK INVENTORY |  |  | TASK COMPLETION LOG
|  |  |  | PROJECTED |  |  | ACTUAL |  |  | TASK COMPLETION (%)
Task ID | DESCRIPTION | WEIGHT (%) | DATE | Task ID | DATA | CUMULATIVE | Task ID | DATA | CUMULATIVE | PROJECTED | ACTUAL
|  |  | 2028-06-28 |  | 0% |  |  | 0% |  | 100% | 100%
|  |  | 2028-06-29 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-06-30 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-01 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-02 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-03 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-04 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-05 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-06 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-07 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-08 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-09 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-10 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-11 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-12 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-13 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-14 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-15 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-16 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-17 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-18 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-19 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-20 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-21 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-22 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-23 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-24 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-25 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
|  |  | 2028-07-26 |  | 0% | 0% |  | 0% | 0% | 100% | 100%
APPLIED WEIGHT % MUST EQUAL 100 > |  | 0%
Formulas:
DATE = [DATE, row above]+1

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.