## EXAMPLE - Advertising Plan
ADVERTISING PLAN TEMPLATE – EXAMPLE
ADVERTISING PLAN
EXECUTIVE SUMMARY |  |  | 1
Describe the advertising plan.
This advertising plan outlines the strategic approach for the upcoming campaign to promote our new product launch. This comprehensive plan encompasses the key objectives, target audiences, chosen advertising channels, creative elements, budget allocation, campaign schedule, and performance metrics.
CAMPAIGN OBJECTIVES |  |  | 2
State the goals and objectives of the advertising campaign.
Within the next quarter, we will achieve a 15 percent increase in website traffic, generate 10,000 new leads, and drive a 20 percent boost in product sales.
TARGET AUDIENCE |  |  | 3
They are 25-40-year-old professionals who work for tech companies and have an interest in productivity tools and software solutions.
ADVERTISING CHANNELS |  |  | 4
List the different advertising channels you will utilize, and describe the rationale behind choosing each.
CHANNEL | OUTLET if applicable | RATIONALE
Social Media | Facebook, LinkedIn | Reach professionals through targeted ads and sponsored posts.
Search Engine Ads | Google Ads | Capture users actively searching for related keywords.
Display Ads | Google Display Network | Utilize visual ads on relevant websites.
Print Media | Industry Magazines | Engage with a niche audience through print ads.
Email Marketing | – | Reach existing subscribers with tailored offers.
Influencer Partnerships | – | Collaborate with industry influencers to amplify reach.
CREATIVE ELEMENTS |  |  | 5
List the creative assets, such as visuals, copy, taglines, and messages, that you will use in the campaign.
ELEMENT | DESCRIPTION
Visuals | Use engaging visuals that highlight the product’s features and benefits.
Copy | Use persuasive copy that focuses on solving pain points and offering solutions.
Tagline | "Empower Your Workflow with [Product Name]"
Message | "Boost productivity and streamline your tasks with our innovative solution."
BUDGET ALLOCATION |  |  | 6
Provide a budget breakdown that illustrates the allocation of funds to each advertising channel. By doing this, you can then manage and distribute your resources efficiently.
CHANNEL | AMOUNT | % of TOTAL
Social Media | 15000 | 30%
Search Engine Ads | 12500 | 25%
Display Ads | 7500 | 15%
Print Media | 5000 | 10%
Email Marketing | 5000 | 10% | TOTAL BUDGET
Influencer Partnerships | 5000 | 10% | 50000
CAMPAIGN SCHEDULE |  |  | 7
Create a timeline that indicates when you will execute each phase of the campaign, from planning and creative development to launch and evaluation.
PHASE |  | TIMELINE
Planning and Creative Development |  | Weeks 1 - 2
Content Creation and Approval |  | Weeks 3 - 4
Pre-Launch Teasers |  | Weeks 5 - 6
Campaign Launch |  | Week 7
Ongoing Monitoring and Optimization |  | Weeks 8 - 12
PERFORMANCE METRICS |  |  | 8
Outline the key performance indicators (KPIs) that you will use to measure the campaign's success. Include metrics like click-through rates, conversions, and ROI.
METRIC |  | TARGET
Click-Through Rate (CTR) |  | 3%
Conversion Rate |  | 10%
Return on Investment (ROI) |  | Targeting 400%
CONTINGENCY PLANS |  |  | 9
Identify potential challenges or issues that might arise and how you will address them to ensure a smooth campaign execution.
In case of low engagement on social media, we'll allocate more of the budget to higher-performing channels, and we’ll adjust our ad creatives to increase relevance.
ROLES AND RESPONSIBILITIES |  |  | 10
Specify who is responsible for various tasks, from creative development to campaign monitoring and analysis.
ROLES | RESPONSIBILITIES
Marketing Manager | Overall campaign strategy and coordination.
Creative Team | Development of visuals, copy, and taglines.
Digital Marketing Specialist | Execution of digital advertising efforts.
Sales Team | Lead management and follow-up.
COMPETITOR ANALYSIS |  |  | 11
Analyze your competitors' strategies and positioning, enabling the campaign to stand out in the market.
Competitor X focuses on price, while Competitor Y emphasizes features. Our campaign positions our product as the perfect balance between affordability and advanced functionality.
LEGAL AND COMPLIANCE |  |  | 12
Address legal and regulatory considerations, ensuring that the campaign adheres to relevant standards.
Ensure that all advertising materials comply with industry regulations and our company's ethical standards.
APPROVAL PROCESS |  |  | 13
Detail the steps and stakeholders involved in reviewing and approving the campaign strategy and creative materials.
The Marketing Manager, Creative Team, and Legal Department will review and give final approval to the campaign strategy.
BRAND GUIDELINES |  |  | 14
Describe the process of integrating brand guidelines in order to ensure consistency in messaging and visuals.
We will adhere to brand guidelines throughout the campaign to ensure consistency in messaging, visuals, and tone.
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Advertising Plan
ADVERTISING PLAN TEMPLATE
ADVERTISING PLAN
EXECUTIVE SUMMARY |  |  | 1
Describe the advertising plan.
CAMPAIGN OBJECTIVES |  |  | 2
State the goals and objectives of the advertising campaign.
TARGET AUDIENCE |  |  | 3
ADVERTISING CHANNELS |  |  | 4
List the different advertising channels you will utilize, and describe the rationale behind choosing each.
CHANNEL | OUTLET if applicable | RATIONALE
CREATIVE ELEMENTS |  |  | 5
List the creative assets, such as visuals, copy, taglines, and messages, that you will use in the campaign.
ELEMENT | DESCRIPTION
Visuals
Copy
Tagline
Message
BUDGET ALLOCATION |  |  | 6
Provide a budget breakdown that illustrates the allocation of funds to each advertising channel. By doing this, you can then manage and distribute your resources efficiently.
CHANNEL | AMOUNT | % of TOTAL
Social Media | 0 | –
Search Engine Ads | 0 | –
Display Ads | 0 | –
Print Media | 0 | –
Email Marketing | 0 | – | TOTAL BUDGET
Influencer Partnerships | 0 | – | 0
CAMPAIGN SCHEDULE |  |  | 7
Create a timeline that indicates when you will execute each phase of the campaign, from planning and creative development to launch and evaluation.
PHASE |  | TIMELINE
PERFORMANCE METRICS |  |  | 8
Outline the key performance indicators (KPIs) that you will use to measure the campaign's success. Include metrics like click-through rates, conversions, and ROI.
METRIC |  | TARGET
CONTINGENCY PLANS |  |  | 9
Identify potential challenges or issues that might arise and how you will address them to ensure a smooth campaign execution.
ROLES AND RESPONSIBILITIES |  |  | 10
Specify who is responsible for various tasks, from creative development to campaign monitoring and analysis.
ROLES | RESPONSIBILITIES
COMPETITOR ANALYSIS |  |  | 11
Analyze your competitors' strategies and positioning, enabling the campaign to stand out in the market.
LEGAL AND COMPLIANCE |  |  | 12
Address legal and regulatory considerations, ensuring that the campaign adheres to relevant standards.
APPROVAL PROCESS |  |  | 13
Detail the steps and stakeholders involved in reviewing and approving the campaign strategy and creative materials.
BRAND GUIDELINES |  |  | 14
Describe the process of integrating brand guidelines in order to ensure consistency in messaging and visuals.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.