## Slide 1
Change Management Project Roadmap Template Example
PROJECT ALPHA
PROJECT MANAGER | Sarah Goodwin | START DATE | MM/DD/YY
OVERALL PROGRESS | 60% as of August 20XX | END DATE | MM/DD/YY
PROJECT DELIVERABLE
SCOPE STATEMENT
Deliverable: Stakeholder Engagement and Training Program
Description: This deliverable ensures that the team effectively involves and trains all relevant parties in the change process. It includes stakeholder identification and analysis, engagement strategy, training curriculum, implementation schedule, and evaluation metrics.
This project will engage stakeholders and provide comprehensive training programs to facilitate a smooth transition to new digital operations.

## Slide 2
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEPT | OCT | NOV | DEC
TODAY
PHASE 1: Planning / Preparation
PHASE 2: Design / Development
PHASE 3: Implementation / Execution
PHASE 4: Evaluation / Closure
MILESTONES
TASKS
05/05: Training Needs Assessment
01/16:
Kickoff
02/20: Stakeholder Analysis
05/08: Training Curriculum
07/11: Pilot Training Evaluation
09/19: Project Review
08/28: Full-Scale Training
10/22: Training Completed
10/23: Review Session
12/19: Closure Report
Meet with stakeholders to introduce the project and gather input
Test training session effectiveness and make needed adjustments
Rollout training across the organization
Detail project outcomes and engagement
Assemble project team
Tailor training modules to different stakeholder groups
Host engagement sessions
Assess overall impact and lessons learned
Evaluate progress and gather feedback
Determine the skills and knowledge gaps that training must address
Change Management Project Roadmap Example

## Slide 3
DISCLAIMER Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.