## Step Change Mgmt RoadMap
Step Change Management Roadmap Template
CLICK HERE TO CREATE IN SMARTSHEET
CREATE THE NEED FOR CHANGE
CHANGE THE DIRECTION
CHANGE THE BEHAVIOR
CHANGE SUSTAINABILITY
Title
Description
Title
Description
Title
Description
Title
Description
Title
Description
Title
Description
Title
Description
Title
Description

## EXAMPLE - Step Change Mgmt
Step Change Management Roadmap Template Example
CREATE THE NEED FOR CHANGE
CHANGE THE DIRECTION
CHANGE THE BEHAVIOR
CHANGE SUSTAINABILITY
Assess Current State and Identify Gaps
Begin by thoroughly analyzing the organization's current state to pinpoint inefficiencies, problems, and areas for improvement. This step highlights the need for change by providing clear evidence and rationale.
Define Change Vision and Objectives
Establish a clear vision and set specific objectives for the change. Articulate what the organization aims to achieve through the change, and detail the benefits and the overarching goals. This clarity helps motivate stakeholders and guide the entire change process.
Develop Leadership Support and Form a Powerful Coalition
Secure commitment from management and the key stakeholders who will lead the change effort. This coalition should be influential and possess the credibility and power to guide the organization through change.
Craft Communication and Engagement Strategy
Develop a strategy for communicating the change to all stakeholders. Ensure the message is clear and compelling. This strategy should engage employees at all levels and foster a sense of involvement and ownership over the change process.
Design Training and Support Programs
Implement training programs to develop employees' necessary skills and knowledge to embrace the change. Additionally, provide ongoing support and resources to help employees adjust to new methods, tools, or processes.
Implement the Change Management Plan
Roll out the change initiatives according to the planned activities, timelines, and resource allocations. This step involves executing the change and closely managing each stage to ensure the work adheres to the new direction.
Monitor Progress and Manage Resistance
Regularly track the progress of the change initiatives against defined milestones and objectives. Address any resistance from employees by engaging them in dialogue, understanding their concerns, and adapting strategies as necessary to maintain momentum.
Review, Refine, and Institutionalize Changes
Evaluate the change outcomes to ensure they meet the initial objectives. Refine elements of the change that are not working. Integrate the changes into standard practices.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.