## Retrospective Radar EXAMPLE
Agile Retrospective Radar Template Example
INSTRUCTIONS
Radar Chart Data |  | SOURCE
SPOKE / LABEL | DEFINITION | Source 1 | Source 2 | Source 3
Communication Clarity | Goals and tasks were clearly communicated, but the API feature deadline caused some confusion. | 4 | 3 | 4
Detail Precision | Tasks were well-documented, except the logistics tracking feature, which needed more detail. | 3 | 3 | 3
Achievability | Sprint goals were realistic, but integrating the new user feedback system was too ambitious. | 2 | 3 | 2
Backlog Alignment | The backlog reflected current priorities well, though some lower-priority items caused minor disruptions. | 3 | 3 | 2
Collaborative Maintenance | The backlog was updated collaboratively, but some documentation updates were missed. | 3 | 3 | 2
Value Guidance | Efforts enhanced product value, but better prioritization based on customer feedback is needed. | 2 | 3 | 2
Radar Chart
CLICK HERE TO CREATE IN SMARTSHEET
1. The facilitator will customize the radar by adding or removing spokes and labeling each spoke according to the team’s focus areas.
2. The team will collaborate to agree on a clear definition for each label, ensuring a shared understanding of the criteria.
3. Move to the collect phase by having team members individually provide a rating for each spoke based on their assessment of the current sprint, using the agreed-upon definitions as a guide.

## Retrospective Radar BLANK
Agile Retrospective Radar Template
INSTRUCTIONS
Use Other Spoke rows to define new labels. Remove unused Spoke rows and unused Source columns to complete your Radar Chart.
Radar Chart Data |  | SOURCE
SPOKE / LABEL | DEFINITION | Source 1 | Source 2 | Source 3 | Source 4 | Source 5
Communication Clarity | Ensure that all project goals, tasks, and expectations are transparently shared with the entire team.
Detail Precision | Specify that all project elements are sufficiently elaborated to avoid ambiguity and ensure that everyone understands what is required.
Achievability | Confirm that the goals set are realistic and attainable given timeframe and available resources.
Backlog Alignment | Verify that the backlog accurately represents the current priorities, planned work, and team commitments.
Collaborative Maintenance | Emphasize that the backlog and project documentation are regularly updated and refined by the entire team.
Value Guidance | Ensure that all efforts are directed towards enhancing the product’s value and meeting customer needs, focusing on delivering high-impact features and improvements.
Other Spoke 1
Other Spoke 2
Other Spoke 3
Other Spoke 4
Other Spoke 5
Other Spoke 6
Radar Chart
1. The facilitator will customize the radar by adding or removing spokes and labeling each spoke according to the team’s focus areas.
2. The team will collaborate to agree on a clear definition for each label, ensuring a shared understanding of the criteria.
3. Move to the collect phase by having team members individually provide a rating for each spoke based on their assessment of the current sprint, using the agreed-upon definitions as a guide.

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.