## Event Marketing Timeline
EVENT MARKETING TIMELINE
[5 empty] | PHASE TWO |  |  | PHASE THREE |  |  | PHASE FOUR
CAMPAIGN TYPE | ADDITIONAL INFO | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12
National Marketing
Banner Ads | bar: WEEK 1; WEEK 3; PHASE TWO WEEK 5; PHASE THREE WEEK 7; PHASE THREE WEEK 9; PHASE FOUR WEEK 11
Local Marketing
Web Ads | bar: WEEK 1 to PHASE TWO WEEK 5; PHASE THREE WEEK 8; PHASE FOUR WEEK 10; PHASE FOUR WEEK 12
Public Relations
Press Releases | bar: WEEK 3; PHASE THREE WEEK 7; PHASE FOUR WEEK 12
Webinars | bar: WEEK 1; PHASE TWO WEEK 5; PHASE FOUR WEEK 10
Content Marketing
Sponsored Content | bar: WEEK 3; PHASE THREE WEEK 7; PHASE FOUR WEEK 11
Landing Page | bar: WEEK 2; PHASE TWO WEEK 4; PHASE TWO WEEK 6; PHASE THREE WEEK 8; PHASE FOUR WEEK 10; PHASE FOUR WEEK 12
White Papers / ebooks | bar: WEEK 1; PHASE TWO WEEK 5; PHASE THREE WEEK 9
Social Media
Twitter
Facebook
Pinterest | bar: WEEK 2; PHASE TWO WEEK 4; PHASE TWO WEEK 6; PHASE THREE WEEK 8; PHASE FOUR WEEK 10; PHASE FOUR WEEK 12
Instagram
Google+ | bar: WEEK 2; PHASE TWO WEEK 4; PHASE TWO WEEK 6; PHASE THREE WEEK 8; PHASE FOUR WEEK 10; PHASE FOUR WEEK 12
LinkedIn | bar: WEEK 1; WEEK 3; PHASE TWO WEEK 5; PHASE THREE WEEK 7; PHASE THREE WEEK 9; PHASE FOUR WEEK 11
Online
Blog
Website | bar: WEEK 1; WEEK 3; PHASE TWO WEEK 5; PHASE THREE WEEK 7; PHASE THREE WEEK 9; PHASE FOUR WEEK 11
Mobile App | bar: WEEK 2; PHASE TWO WEEK 4; PHASE THREE WEEK 7; PHASE FOUR WEEK 10
Mobile Alerts | bar: WEEK 3; PHASE TWO WEEK 6; PHASE THREE WEEK 9; PHASE FOUR WEEK 12
Email Newsletter
Web
Development | bar: WEEK 1 to WEEK 3
Pay-Per-Click Marketing | bar: PHASE TWO WEEK 5 to PHASE FOUR WEEK 10
SEO | bar: WEEK 2 to PHASE TWO WEEK 5
Market Research
Surveys | bar: WEEK 3; PHASE THREE WEEK 7; PHASE FOUR WEEK 10
Impact Studies | bar: PHASE TWO WEEK 6 to PHASE THREE WEEK 9
Sales Campaigns
Campaign A | bar: WEEK 1 to WEEK 3
Campaign B | bar: PHASE TWO WEEK 4 to PHASE TWO WEEK 6
Campaign C | bar: PHASE TWO WEEK 6 to PHASE THREE WEEK 8
Campaign D | bar: PHASE THREE WEEK 8 to PHASE FOUR WEEK 10
Campaign E | bar: PHASE FOUR WEEK 11 to PHASE FOUR WEEK 12
Other
Corporate Branding | bar: WEEK 2 to PHASE TWO WEEK 4
Click Here to Create a Collaborative Event Marketing Timeline in Smartsheet