## Residential Renovation Timeline
RESIDENTIAL RENOVATION TIMELINE TEMPLATE
PROJECT NAME |  | PROJECT MANAGER |  |  | START DATE
[5 empty] | 2017-09-18 | <--Enter date of Monday of first week.
PRIORITY | TASK NAME | START DATE | END DATE | DURATION | STATUS | PERCENTAGE COMPLETE | ASSIGNED TO | COMMENTS | PRIORITY | STATUS | 2017-09-18 |  |  |  |  | 2017-09-25 |  |  |  |  | 2017-10-02 |  |  |  |  | 2017-10-09 |  |  |  |  | 2017-10-16 |  |  |  |  | 2017-10-23 |  |  |  |  | 2017-10-30 |  |  |  |  | 2017-11-06 |  |  |  |  | 2017-11-13 |  |  |  |  | 2017-11-20 |  |  |  |  | 2017-11-27 |  |  |  |  | 2017-12-04 |  |  |  |  | 2017-12-11 |  |  |  |  | 2017-12-18 |  |  |  |  | 2017-12-25 |  |  |  |  | 2018-01-01 |  |  |  |  | 2018-01-08 |  |  |  |  | 2018-01-15 |  |  |  |  | 2018-01-22 |  |  |  |  | 2018-01-29 |  |  |  |  | 2018-02-05 |  |  |  |  | 2018-02-12 |  |  |  |  | 2018-02-19 |  |  |  |  | 2018-02-26 |  |  |  |  | 2018-03-05 |  |  |  |  | 2018-03-12 |  |  |  |  | 2018-03-19 |  |  |  |  | 2018-03-26 |  |  |  |  | 2018-04-02 |  |  |  |  | 2018-04-09 |  |  |  |  | 2018-04-16 |  |  |  |  | 2018-04-23 |  |  |  |  | 2018-04-30 |  |  |  |  | 2018-05-07 |  |  |  |  | 2018-05-14 |  |  |  |  | 2018-05-21 |  |  |  |  | 2018-05-28 |  |  |  |  | 2018-06-04 |  |  |  |  | 2018-06-11 |  |  |  |  | 2018-06-18 |  |  |  |  | 2018-06-25 |  |  |  |  | 2018-07-02 |  |  |  |  | 2018-07-09 |  |  |  |  | 2018-07-16
| House Remodel | 2017-09-21 | 2018-06-01 | 254 |  | 1% |  |  | KEY | KEY | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
| Start Date | 2017-09-21 | 2017-10-02 | 12 |  | 46% |  |  | Low | Not Started
Medium | Final Estimate Complete | 2017-09-21 | 2017-09-21 | 1 | Complete | 100% |  |  | Medium | In Progress
High | Contract Signed | 2017-09-22 | 2017-09-29 | 8 | Complete | 100% |  |  | High | Complete
Low | Permission to Schedule Work? | 2017-10-02 | 2017-10-02 | 1 | In Progress | 40%
| Demo Prep | 2017-10-03 | 2017-10-06 | 4 |  | 0%
High | Appliance, Fixture, and Salvage | 2017-10-03 | 2017-10-03 | 1 | Complete | 100%
High | Electrical - Cut Power and Install Temp Service | 2017-10-04 | 2017-10-04 | 1 | Not Started | 0%
Medium | Safety Fence Delivery/Setup | 2017-10-05 | 2017-10-05 | 1 | In Progress | 30%
Low | Install Office/Safety Area (Plans Desk, First Aid, Phone) | 2017-10-06 | 2017-10-06 | 1 |  | 0%
Low | Install Site Camera(s) | 2017-10-06 | 2017-10-06 | 1 |  | 0%
| Demolition | 2017-10-06 | 2017-10-25 | 20 |  | 0%
| Scrap the Upper Two Floors | 2017-10-06 | 2017-10-20 | 15 |  | 0%
| Basement Demolition | 2017-10-18 | 2017-10-25 | 8 |  | 0%
| Excavation | 2017-10-25 | 2017-10-29 | 5
| Foundation Prep | 2017-10-25 | 2017-10-27 | 3
| Oil Tanks | 2017-10-25 | 2017-10-27 | 3
| Backfill | 2017-10-29 | 2017-10-29 | 1
| Concrete | 2017-11-01 | 2017-11-15 | 15
| Footings, Walls, and Pads | 2017-11-01 | 2017-11-08 | 8
| Slabs | 2017-11-10 | 2017-11-15 | 6
| Pre Backfill | 2017-11-13 | 2017-11-18 | 6
| Drainage | 2017-11-18 | 2017-11-18 | 1
| Waterproofing | 2017-11-13 | 2017-11-13 | 1
| Framing | 2017-10-25 | 2017-12-08 | 45
| Level/True Basement and Main Floor | 2017-10-25 | 2017-10-27 | 3
| Frame New Home and Addition | 2017-11-18 | 2017-12-08 | 21
| Roof | 2017-11-19 | 2017-12-08 | 20
| Dry In Roof - IWS and Felt | 2017-11-29 | 2017-11-29 | 1
| Upper Roofing | 2017-11-26 | 2017-12-08 | 13
| Flat Roofs | 2017-11-19 | 2017-11-24 | 6
| Plumbing | 2017-10-29 | 2017-12-08 | 41
| Ground Work | 2017-10-29 | 2017-11-01 | 4
| Rough In | 2017-11-29 | 2017-12-08 | 10
| Windows | 2017-11-22 | 2017-12-15 | 24
| Order Windows | 2017-11-22 | 2017-11-24 | 3
| Wrap Sills | 2017-11-29 | 2017-12-01 | 3
| Install Windows | 2017-12-08 | 2017-12-15 | 8
| HVAC | 2017-11-29 | 2017-12-20 | 22
| Ducting and Gas Piping | 2017-11-29 | 2017-12-06 | 8
| Fire System for Drywall | 2017-12-20 | 2017-12-20 | 1
| Electrical | 2017-12-10 | 2017-12-20 | 11
| Electrical - Rough In | 2017-12-10 | 2017-12-20 | 11
| Walkthrough | 2017-12-17 | 2017-12-17 | 1
| A/V | 2017-12-10 | 2017-12-18 | 9
| Low Voltage - CATV, CAT6, Tele | 2017-12-10 | 2017-12-13 | 4
| Speaker Pre-Wire | 2017-12-18 | 2017-12-18 | 1
| Alarm/Security Wiring | 2017-12-13 | 2017-12-13 | 1
| House Wrap | 2017-12-27 | 2017-12-29 | 3
| House Wrap | 2017-12-27 | 2017-12-29 | 3
| Insulation | 2017-12-03 | 2017-12-21 | 19
| Blow In | 2017-12-03 | 2017-12-03 | 1
| Bats | 2017-12-21 | 2017-12-21 | 1
| Rigid | 2017-12-21 | 2017-12-21 | 1
| Drywall | 2018-01-03 | 2018-12-23 | 355
| Delivery | 2018-01-03 | 2018-01-03 | 1
| Hang and Scrap | 2018-12-21 | 2018-12-21 | 1
| Tape | 2018-12-21 | 2018-12-21 | 1
| Prime | 2018-12-23 | 2018-12-23 | 1
| Touch Up If Needed | 2018-12-23 | 2018-12-23 | 1
| Exterior Stone | 2018-01-03 | 2018-01-17 | 15
| Back Patio | 2018-01-03 | 2018-01-12 | 10
| Back Entry | 2018-01-17 | 2018-01-17 | 1
| Exterior Case Work | 2018-01-04 | 2018-01-15 | 12
| Trim Windows | 2018-01-04 | 2018-01-15 | 12
| Siding | 2018-01-04 | 2018-01-15 | 12
| Laundry/Furnace Room Flooring | 2018-02-16 | 2018-03-13 | 26
| Install and Stay Off | 2018-02-16 | 2018-03-13 | 26
| Hardwoods | 2018-01-19 | 2018-03-09 | 50
| Deliver/Acclimate | 2018-02-28 | 2018-03-09 | 10
| Install Hardwoods | 2018-01-25 | 2018-01-29 | 5
High | Stain | 2018-01-25 | 2018-01-29 | 5
High | Finish | 2018-01-19 | 2018-02-16 | 29
| Cure and Protect | 2018-01-19 | 2018-01-19 | 1
| Tile | 2018-02-03 | 2018-02-17 | 15
| Prep | 2018-02-03 | 2018-02-05 | 3
| Install | 2018-02-07 | 2018-02-09 | 3
| Install | 2018-02-17 | 2018-02-17 | 1
| Cabinets | 2018-01-18 | 2018-03-09 | 51
| Master Bath | 2018-01-18 | 2018-01-22 | 5
| Upper Floor Bathrooms | 2018-01-19 | 2018-02-02 | 15
| Kids' Built-Ins | 2018-02-16 | 2018-02-23 | 8
| Upper Floor Built Ins | 2018-02-18 | 2018-03-09 | 20
| Kitchen | 2018-02-21 | 2018-02-21 | 1
| Main Floor | 2018-02-23 | 2018-02-23 | 1
| Basement | 2018-02-18 | 2018-02-18 | 1
| Plumbing Hang Sinks | 2018-02-16 | 2018-02-23 | 8
| Install under Mount Sinks | 2018-02-16 | 2018-02-23 | 8
| Interior Doors | 2018-02-25 | 2018-03-08 | 12
| Delivery-Hang | 2018-03-03 | 2018-03-08 | 6
| Ship to Pre-Fin | 2018-02-25 | 2018-02-25 | 1
| Millwork | 2018-02-18 | 2018-02-20 | 3
| Millwork Material Delivery | 2018-02-18 | 2018-02-20 | 3
| Millwork Install | 2018-02-18 | 2018-02-18 | 1
| Interior Painting | 2018-02-28 | 2018-04-17 | 49
| Millwork Prep | 2018-02-28 | 2018-03-16 | 17
| Cleaning and Masking | 2018-02-28 | 2018-02-28 | 1
| Millwork Painting and Curing (Oil) | 2018-02-28 | 2018-03-16 | 17
| Interior Walls and Ceilings | 2018-03-18 | 2018-04-17 | 31
| Stone Counters | 2018-03-21 | 2018-03-30 | 10
| Templating | 2018-03-21 | 2018-03-21 | 1
| Install | 2018-03-22 | 2018-03-30 | 9
| Schedule Buffer | 2018-02-28 | 2018-03-09 | 10
| Decks | 2018-02-28 | 2018-03-20 | 21
| Decking | 2018-02-28 | 2018-02-28 | 1
| Railings | 2018-03-16 | 2018-03-20 | 5
| Interior Doors Hang and Hardware | 2018-05-03 | 2018-05-15 | 13
| Return from Pre-Fin Shop | 2018-05-03 | 2018-05-14 | 12
| Hang | 2018-05-03 | 2018-05-10 | 8
| Install Hardware | 2018-05-11 | 2018-05-15 | 5
| Appliances | 2018-05-02 | 2018-05-03 | 2
| Delivery | 2018-05-02 | 2018-05-02 | 1
| Install | 2018-05-03 | 2018-05-03 | 1
| Plumbing | 2018-05-02 | 2018-05-04 | 3
| Set Toilets, Sinks, etc. | 2018-05-02 | 2018-05-04 | 3
| Electrical | 2018-05-03 | 2018-05-11 | 9
| Trim Cans | 2018-05-03 | 2018-05-07 | 5
| Outlets and Switches | 2018-05-04 | 2018-05-11 | 8
| Surface Mount Fixtures | 2018-05-04 | 2018-05-11 | 8
| Bathroom Glass | 2018-05-09 | 2018-05-15 | 7
| Mirrors | 2018-05-11 | 2018-05-15 | 5
| Shower Doors | 2018-05-09 | 2018-05-09 | 1
| Garage Door Dress Up | 2018-05-13 | 2018-05-16 | 4
| Final Inspections | 2018-05-02 | 2018-05-02 | 1
| Plumbing, Electrical, Mechanical | 2018-05-02 | 2018-05-02 | 1
| Final Inspection | 2018-05-02 | 2018-05-02 | 1
| Wrap Up | 2018-05-09 | 2018-06-06 | 29
| Punch List and Touch Up | 2018-05-23 | 2018-05-25 | 3
| Bath Accessories | 2018-05-23 | 2018-05-23 | 1
| Remove Tools | 2018-05-25 | 2018-05-29 | 5
| Remove Materials | 2018-05-09 | 2018-06-06 | 29
| Deliver Job Book (Sub List, Warranty/Install Paperwork, etc.) | 2018-05-23 | 2018-05-25 | 3
| Deliver Keys and Garage Remotes | 2018-05-09 | 2018-05-09 | 1
| House Cleaning | 2018-05-29 | 2018-06-08 | 11
| Yard | 2018-05-30 | 2018-05-30 | 1
| Home | 2018-06-03 | 2018-06-06 | 4
| Garage | 2018-06-08 | 2018-06-08 | 1
| Windows | 2018-05-29 | 2018-06-08 | 11
| Complete | 2018-06-01 | 2018-06-01 | 1
CLICK HERE TO CREATE A RESIDENTIAL RENOVATION TIMELINE TEMPLATE IN SMARTSHEET
Formulas:
PROJECT MANAGER = [PROJECT MANAGER, row below]
TODAY